# Guidelines: Work Breakdown Structures

## Topics:

- Introduction

- Coarse-Grained vs Fine-Grained Plans

- Project (Coarse-Grained) WBS Structure

- Iteration (Fine-Grained) WBS Structure

## Introduction

A good work breakdown structure (WBS) and its synchronization with the process framework are critical success factors in software project success.  A work breakdown structure provides a structure for the following information:

- A delineation of all significant work

- A clear task decomposition for assignment of responsibilities

- A framework for scheduling, budgeting, and expenditure tracking

Conventional work breakdown structures frequently suffer from three fundamental flaws:

- They are prematurely structured around the product design

Once a structure that is based on the product design is ingrained in the WBS, a concrete planning foundation has been set that is difficult and expensive to change.  To couple the plan tightly to the product structure may make sense if both are reasonability mature.  However, a looser coupling is desirable if either the plan or the architecture is subject to change.

- They are prematurely decomposed, planned and budgeted in either to much or too little detail.

In general, a WBS elaborated to at least two or three levels makes sense.  For larger scale systems, additional levels may be necessary in later phases of the lifecycle.  The basic problem with planning too much detail at the outset is that the detail does not evolve with the level of fidelity in the plan.  For example, it is impossible to layout accurately in month 1 – when the plan is being baselined, and before the architecture and test scenarios have been engineered – details of the test activities that are scheduled 18 months later.

- They are project-specific, and cross project comparisons are usually difficult or impossible.

With no standard WBS structure, it is extremely difficult to compare plans, financial data, schedule data, organizational efficiencies, cost trends, productivity trends, or quality trends across multiple projects.  A standard WBS structure is also required to leverage historical data to for project estimation.

These guidelines are designed to address the flaws indicated above and to position the project team for success in applying RUP.

## Coarse-Grained vs Fine-Grained Plans

In an iterative process, two kinds of plans are recommended:

- A coarse-grained plan.  The project plan, which focuses on phases and iterations, their objectives, and the overall staffing level.

There is only one project plan per development project.  It acts as the overall “envelope” of the project for one cycle (Release).  It is produced very early in the inception phase and updated as often as necessary.

- A series of fine-grained plans.  The iteration plans, one per iteration, which bring RUP activities and individual resources into perspective.

An iteration plan is a fine-grained, time-boxed plan; there is one plan per iteration.  As the iteration plan focuses on only one iteration, it has a time span small enough that it provides the team members with the insight to do the kind of detailed planning that they are familiar with.  It is the basis of allocation of tasks to project team members.

## Project (Coarse-Grained) WBS Structure

The WBS hierarchy for the coarse-grained project plan is as follows:

- First-level WBS elements are defined for each phase of the lifecycle (inception, elaboration, construction, and transition)

- Second-level WBS elements are defined for each iteration in the phase.  The naming standard for the iteration is as follows:

  - Inception Phase Iterations are termed Inception Iteration 1 through Inception Iteration n – were n is the total number of iterations in the Inception Phase

  - Elaboration Phase Iterations are termed Elaboration Iteration 1 through Elaboration Iteration n – were n is the total number of iterations in the Elaboration Phase

  - Construction Phase Iterations are termed Construction Iteration 1 through Construction Iteration n – were n is the total number of iterations in the Construction Phase

  - Transition Phase Iterations are termed Transition Iteration 1 through Transition Iteration n – were n is the total number of iterations in the Transition Phase

Each Iteration should have information (a note/attached document) which outlines the planned scope and objectives of the iteration.

### Example Project (Coarse-Grained) WBS Structure:

## Iteration (Fine-Grained) WBS Structure

The WBS hierarchy for the fine-grained iteration plan is as follows:

- First-level WBS elements are defined for each iteration in the phase.  The naming standard for the iteration is as follows:

  - Inception Phase Iterations are termed Inception Iteration 1 through Inception Iteration n – were n is the total number of iterations in the Inception Phase

  - Elaboration Phase Iterations are termed Elaboration Iteration 1 through Elaboration Iteration n – were n is the total number of iterations in the Elaboration Phase

  - Construction Phase Iterations are termed Construction Iteration 1 through Construction Iteration n – were n is the total number of iterations in the Construction Phase

  - Transition Phase Iterations are termed Transition Iteration 1 through Transition Iteration n – were n is the total number of iterations in the Transition Phase

- Second-Level WBS Elements are defined for each RUP discipline (Business Modeling, Requirements, Analysis & Design, Implementation, Test, Deployment, Configuration & Change Management, Project Management, and Environment) that is in the scope of the iteration.

  - Exception to the rule: A project team may be organized into sub-teams with each sub-team being responsible for a defined scope that crosses multiple RUP disciplines.  When this occurs, the sub-team becomes the  second-level WBS Element.  The RUP Disciplines used by the sub-team will become the 3rd level WBS elements under the sub-team.

### Example Iteration (Fine-Grained) WBS Structure

### Example Iteration (Fine-Grained) WBS Structure with sub-teams

### Additional Recommendations for the Fine-Grained Plan

In practice, lower levels of the WBS will vary in accordance with the needs of the project.  However, the following guideline should be considered:

- RUP disciplines are organized by workflows which are comprised of workflow details which are comprised of a set of activities which contain a number of steps.   In general, 3rd level (4th level with sub-teams) and below WBS elements should align with this structure to the degree possible.  For example, the WBS structure to depict the work required to define a Candidate architecture may be as follows: