## Staffing
S.No. | Task(s) | Start Date | End Date | Responsible Role | Participant Role | Comments | Deliverable
1 | Identify Mentors
1.1 | From each BU, identify few SMEs in requirements management | W8.Mon | W8.Fri | CoC Coordinator, BU Lead | Project Manager/Technical Leaders
1.2 | Get the buy-in from BU leader, delivery leader and project manager for these folks to become mentors | W8.Mon | W8.Fri | CoC Coordinator, BU Lead | BU Leaders/Delivery Heads
2 | Develop Mentors
2.1 | Participate in Train the trainer program | W9.Mon | W10.Fri | SMEs
2.2 | Get training certification | W11.Mon | W11.Fri | SMEs
2.3 | Participate in mentoring sessions | W9.Mon | W10.Fri | SMEs
2.4 | Work with the Mentor and learn which assets to develop in mentoring sessions | W11.Mon | W11.Fri | SMEs
2.5 | Learn how to assess progress of adoption | W11.Mon | W11.Fri | SMEs
2.6 | Learn how to assess progress of skill development | W11.Mon | W11.Fri | SMEs

## Evangelize
S.No. | Task(s) | Start Date | End Date | Responsible Role | Participant Role | Comments | Deliverable
1 | Generate Demand and build a pipeline of projects who are interested in adopting the Requirements Management practice and IBM ReqPro
1.1 | Meet with Business Unit heads/Delivery leader in Business Unit 1 | W1.Mon | W1.Mon | CoC Coordinator | BU leader/Delivery Heads
1.2 | Meet with Business Unit heads/Delivery leader in BU 2 | W1.Tues | W1.Tues | CoC Coordinator | BU leader/Delivery Heads
1.3 | Meet with Business Unit heads/Delivery leader in BU 3 | W1.Wed | W1.Wed | CoC Coordinator | BU leader/Delivery Heads
1.4 | Meet with Project/Program Managers in BU 4 | W1.Mon | W1.Mon | CoC Coordinator | Project/Program Managers
1.5 | Meet with Project/Program Managers in BU 5 | W1.Tues | W1.Tues | CoC Coordinator | Project/Program Managers
1.6 | Meet with Project/Program Managers in BU 6 | W1.Wed | W1.Wed | CoC Coordinator | Project/Program Managers
2 | Raise General awareness of the Requirements Management practice and ReqPro
2.1 | Organize Road Show to create awareness | Bi-weekly
2.2 | Organize technical chats every week or alternate week | Bi-weekly |  |  |  | When thre is critical mass, this can be weekly event
2.4 | Organize lunch & learn sessions ( face to face sessions ) to create awareness | Bi-weekly |  |  |  | When thre is critical mass, this can be weekly event

## Deployment&Adoption
S.No. | Task(s) | Start Date | End Date | Responsible Role | Participant Role | Comments | Deliverable
1 | Plan
1.1 | Create a Plan for Deployment and Adoption (D&A Plan) for the project. | W3.Mon | W3.Tues | CoC Coordinator, mentor | Project Manager
1.2 | Review the project plan and align the dates for D&A Plan with the project plan | W3.Tues | W3.Wed | CoC Coordinator, mentor | Project Manager
2 | Deployment
2.1 | Quick Review the current process used by the team | W3.Wed | W3.Wed | CoC Coordinator, mentor | Technical Leader(s)
2.2 | Adjust the "Usage Model" if needed | W3.Wed | W3. Thurs | CoC Coordinator, mentor | Technical Leader(s)
2.3 | Adjust the "Tool Configuration" if needed | W3.Thurs | W3.Fri | CoC Coordinator, mentor | Technical Leader(s)
2.4 | Repeat 2.1-2.3 for all "process and tools areas" in scope for the project
3 | Adoption
3.1 | Identify the assets that will be used for training and mentoring | W4.Mon | W4.Mon | CoC Coordinator, mentor
3.2 | Provide training sessions in the tools and process areas | W4.Mon | W4.Fri | CoC Coordinator, mentor | Project Team
3.3 | Provide mentoring sessions or workshops in the tools and process areas for the project team | W5.Mon | W5.Wed | Mentor | Project Team
3.4 | Review the "Artifacts" created by the project team using the tools | W5.Thurs | W5.Fri | Mentor | Project Team
3.5 | Repeat 3.1-3.4 for all "process and tools areas" in scope for the project
3.6 | Determine if the existing assets need be eveolved | W5.Fri | W5.Fri | CoC Coordinator
3.7 | Determine if new assets needs to be created | W5.Fri | W5.Fri | CoC Coordinator

## Assessment
S.No. | Task(s) | Start Date | End Date | Responsible Role | Participant Role | Comments | Deliverable
1 | Assess the strength and weakness (opportunity for improvement) for a project
1.1 | Project 1: Meet with the Project Manager and understand the areas of improvement in the project (from SDLC process and tool perspective | W2.Mon | W2.Mon | CoC Coordinator | Project Manager
1.2 | Project 1: Meet with Technical Leader(s) for each area where where there is opportunity for improvement | W2.Mon | W2.Mon | CoC Coordinator | Technical Leader(s)
1.3 | Project 2: Meet with the Project Manager and understand the areas of improvement in the project (from SDLC process and tool perspective | W2.Tues | W2.Tues | CoC Coordinator | Project Manager
1.4 | Project 2: Meet with Technical Leader(s) for each area where where there is opportunity for improvement | W2.Tues | W2.Tues | CoC Coordinator | Technical Leader(s)
1.5 | Project 3: Meet with the Project Manager and understand the areas of improvement in the project (from SDLC process and tool perspective | W2.Wed | W2.Wed | CoC Coordinator | Project Manager
1.6 | Project 3: Meet with Technical Leader(s) for each area where where there is opportunity for improvement | W2.Wed | W2.Wed | CoC Coordinator | Technical Leader(s)
1.7 | Project 4: Apply Self Check process to perform project assessment | W2. Thurs | W2. Thurs | CoC Coordinator | Project Team
1.8

## Asset Evolution
S.No. | Task(s) | Start Date | End Date | Responsible Role | Participant Role | Comments | Deliverable
1 | Develop Re-usable Asset
1.1 | Identify the needs from Project Managers/Technical Leaders/CoEs | W6.Mon | W6.Tues | CoC Coordinator | Technical Leader(s)
1.2 | Identify the needs from Project teams that received training/mentoring | W6.Wed | W2.Wed | CoC Coordinator | Technical Leader(s)
1.3 | Create assets by harvesting best practices from project teams | W6.Mon | W6.Fri | Mentor, CoC Coordinator | Technical Leader(s)
2 | Evolve the assets
2.1 | Based on the lessons learned from projects, evovle the assets | W6.Wed | W6.Wed | Mentor, CoC Coordinator | Technical Leader(s)
2.2 | Create variations of the assets based on the specific Bus/verticals | W7. Thurs | W7. Thurs | Mentor, CoC Coordinator | Technical Leader(s)

## Measurements-Lessons Learnt
S.No. | Task(s) | Start Date | End Date | Responsible Role | Participant Role | Comments | Deliverable
1 | Collect Measurements
1.1 | For each project adopting new capabilities, collect the measures in respective tools ( Requirements Churn, Untraced Requirements, Release Burndown, Requirements Status Trend) | W12.Mon | W12.Mon | mentor/ pm | Project Team
1.2 | Analyze the control measures and determine "outcome measures" | W12.Tues | W12.Tues
1.3 | Compare the actual outcome measures against target | W12.Tues | W12.Tues
1.4 | Collect the adoption measures | W12.Wed | W12.Wed |  | Project Team
1.5 | Comare the adoption measures against target | W12.Wed | W12.Wed
2 | Lessons Learned
2.1 | Collect feedback on the effectiveness of the assests | W12.Mon | W12.Mon |  | Project Team
2.2 | Collect feedback on the effectivness of the tools | W12.Tues | W12.Tues |  | Project Team
2.3 | Collect feedback on the effectiveness of training sessions | W12.Wed | W12.Wed |  | Project Team
2.4 | Collect feedback on the effectiveness of mentoring sessions/workshops | W12.Thurs | W12.Thurs |  | Project Team