## WebSphere
WebSphere
Status | Project # | Project Name | Presentation Workbook Pub Date | Lab WorkBook Pub Date | Images Pub Date | AV Demo | Instructor's Guide | Launch prz Pub Date | Flyer | Abstract | Announce Date | PSN | Resource name | Manager Name | IDS Contact | Conf Call Setup | Update Event System | PoT Catalog Update
Active | W1 | WID/WPS | 2006-03-15 | 2006-02-24 | 2006-02-24 | 2006-02-24 | 2006-02-24 | 2006-02-17 | 2006-02-24 | 2006-02-24 | 2006-02-24 |  | Neil Kolban | Edward Duhe | Dan Ayala | N | No | No
Complete | W2 | WPG | Discovering the Value of WebSphere Partner Gateway v6 for Your Organization | 2006-01-26 | 2006-01-26 | 2006-01-26 | 2006-01-13 | 2006-01-26 | 2006-01-11 | 2006-01-11 | 2006-01-11 | ASAP | Doug Hillary | Edward Duhe | Dan Ayala | 2006-01-26 | ? | 2006-01-26
Active | W3 | Monitor | 2006-04-30 | 2006-04-30 | 2006-04-30 | 2006-04-30 | 2006-04-30 | 2006-04-30 | 2006-04-30 | 2006-04-30 | 2006-04-30 |  | John Dudley Bob Hartley | Edward Duhe | Dan Ayala | N | N | No
Complete | W4 | Modeler V6 | 2006-01-31 | 2006-01-31 | 2006-01-31 | 2/15/06(Cam) | 2006-01-31 | 2006-01-31 | 2006-01-31 | 2006-01-31 | 2006-02-03 |  | John Rollings | Edward Duhe | Dan Ayala | 2/9/2006 (10:AM) | WebSphere Business Modeler | Publish and Sunset the Modeler/Monito
Active | W5 | WebSphere ESB | 2006-03-15 | 2006-03-15 | 2006-03-15 | 2006-03-15 | 2006-03-15 | 2006-03-15 | 2006-03-15 | 2006-03-15 | 2006-03-15 |  | Tom Watson | Edward Duhe | Dan Ayala | N - 03-09-2006 |  | No
Active | W6 | Process Integration V6.01 Update | 2006-03-20 | 2006-03-20 | 2006-03-20 | 2006-03-20 | 2006-03-20 | 2006-03-20 | 2006-03-20 | 2006-03-20 | ???? |  | Greg Piamonte
Complete | W7 | EGL | 2006-01-20 | 2005-11-30 | 2006-01-20 | 2006-01-20 | 2006-01-20 |  | 2006-01-20 | 2006-01-20 | 2006-01-20 |  | Reginaldo Barosa | Michael Spano | Dan Ayala | n | No | No
Active | W8 | Contact Center Voice Pervasive (Voice Update) | 2006-03-30 | [9 empty] | Chuck Carson
Planned | W9 | WAS ND V6.1 Update | 2006-06-29 | [9 empty] | Selorm Agudu
Active | W10 | WebSphere XD 6.01 Update | 2006-03-30 | [9 empty] | Cary Wright
Complete | W11 | WDz 6.1 Update | 2006-02-20 | 2006-02-20 | 2006-02-20 | 2006-02-20 | 2006-02-20 | 2006-02-20 | 2006-02-20 | 2006-02-20 | 2006-02-20 |  | Reinaldo Baroso | Michael Spano | Dan Ayala | N | N | N
Complete | W12 | Hats 6.01 Update | 2006-01-23 | 2006-01-23 | 2006-01-23 | 2006-01-23 | 2006-01-23 | 2006-01-23 | 2006-01-23 | 2006-01-23 | ?? |  | Meshach Baptist | Michael Spano | Dan Ayala | N | N | N
Active | ePoC1 | ITCAM/WAS/RAD | 2006-03-30 | 2006-02-28 | [6 empty] | ??? |  | Norm Smith
Complete | ePoC2 | BI - Scenarios 1 | [10 empty] | ISSW
Complete | ePoC3 | BI - Scenarios 2 | [10 empty] | ISSW
Complete | ePoC4 | BI - Scenarios 3 | [10 empty] | ISSW
Complete | ePoC5 | BI - Scenario 4 | [10 empty] | ISSW
Complete | ePoC6 | BI - Scenario 5 | [10 empty] | ISSW
Complete | ePoC7 | BI - Scenario 6 | [10 empty] | ISSW
Complete | ePoC8 | BI - Scenario 7 | [10 empty] | ISSW
Complete | ePoC9 | BI - Scenario 8 | [10 empty] | ISSW
Complete | ePoC10 | BI - Scenario 9 | [10 empty] | ISSW
Planned | Scenario3 (Updated)
Planned |  | WESB
Planned |  | MBv6
Active | WCEP1 | PI | [10 empty] | Dominque
Complete | EoTW1 | SoA | 2006-02-28 | 2006-02-28 | 2006-02-28 | 2006-02-28 | ???? | 2006-02-28 | 2006-02-28 | 2006-02-28 | 2006-02-28 | 2006-02-28 | 2006-02-28 | 2006-02-28 | 2006-02-28 | 2006-02-28

## IM
Information Management
Status | Project # | Project Name | Presentation Workbook Pub Date | Lab WorkBook Pub Date | Images Pub Date | AV Demo | Instructor's Guide | Launch prz Pub Date | Flyer | Abstract | Announce Date | PSN | Resource name | Manager Name | IDS Contact | Conf Call Setup | Update Event System | PoT Catalog Update
Active | IM1 | ECM Full Stack | 2006-04-15 | 2006-04-15 | 2006-04-15 | 2006-04-15 | 2006-04-15 | 2006-03-15 | 2006-03-15 | 2006-03-15 | 3/24006 |  | Bob | Scot Rich | Mitch Odum | 3/31/2006 11:00 - 11:30 | N | N
Active | IM2 | Omnifind (Update) | 2006-02-27 | [9 empty] | Rincy | Roxane
Active | IM3 | DB2 for Sql | 2006-02-13 | 2006-02-13 | 2006-02-13 |  | 2006-02-13 | 2006-02-13 | 2006-02-13 | 2006-02-13 | 2006-02-13 |  | Vikrim
Active | IM4 | DB2 for Oracle DBA (XML for DB2) Update | [10 empty] | Monty Wright
Active | IM5 | DB2 - Avokia | 2006-02-17
Active | IM6 | DB2 - xKoto | 2006-03-10 | [9 empty] | Monty
Active | IM7 | DB2 XML | 2006-04-30 | [9 empty] | Monty
Active | IM8 | HADR (Update) | 2006-02-28
Active | IM EOT | OmniFind | 2006-02-27 | [10 empty] | Roxane
Active |  | WebSphere II | 2006-02-24

## Tivoli
Tivoli
Status | Project # | Project Name | Presentation Workbook Pub Date | Lab WorkBook Pub Date | Images Pub Date | AV Demo | Instructor's Guide | Launch prz Pub Date | Flyer | Abstract | Announce Date | PSN | Resource name | Manager Name | IDS Contact | Conf Call Setup | Update Event System | PoT Catalog Update
Complete | TI02 | SVC | 2005-12-15 | 2005-12-15 | 2005-12-15 |  | 2005-12-15 | 12/15/2005 - 10:30 | 2005-11-28 | 2005-11-28 | 2005-12-12 |  | Gary Landon | Don Dishinger | Ursual Delaine
Planned | TI03 | LCM |  | ????
Active | Ti04 | Security |  | 2005-10-31 | [8 empty] | David Ballard | Gordon Nellis/Minneapolis/IBM | Ursual Delaine
Complete | TI05 | ITM | 2005-12-05 | 2005-12-05 | 2005-12-05 |  | 2005-12-05 | 2005-11-28 | 2005-11-28 | 2005-11-28 | 2006-12-01 |  | Gary Neal | Gordon Nellis/Minneapolis/IBM | Ursual Delaine
Active | Ti06 | FIM |  | 2006-04-01 | [8 empty] | David Ballard
Active | TI07 | BSM Update |  | 2006-04-15 | [8 empty] | Rod Bowman
Planned | TI08 | Omegamon Z |  | 2006-03-30 | [8 empty] | Lih M Wang/Chicago/IBM
Complete | T109 | TPC | 2006-03-15 | 2006-03-15 | 2006-03-15 | 2006-03-15 | 2006-03-15 | 2006-03-15 | 2006-03-15 | 2006-03-15 | 2006-03-15 |  | Patrick Hassett Jr/Seattle/IBM | Gordon Nellis/Minneapolis/IBM | Ursual Delaine
Planned | TI10 | OMEGAMON - ITCAM(Automation CEP) | 2006-05-15 | [9 empty] | Chris Smit/Gary Neal
Planned | TI11 | TIM Express (Security CEP) | 2006-05-15 | [9 empty] | Beth Melvin
Complete | TCEP1 | Security
Complete | TCEP2 | SVCCEP | 2005-12-05
Complete | TCEP3 | Automation CEP
Active | TEoT1 | Automation -TIO | 2006-02-10
Active | TEO2 | Autiomation - ITM | 2006-02-10
Complete | TE03 | ILM | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02

## Rational
Rational
Status | Project # | Project Name | Presentation Workbook Pub Date | Lab WorkBook Pub Date | Images Pub Date | AV Demo | Instructor's Guide | Launch prz Pub Date | Flyer | Abstract | Announce Date | PSN | Resource name | Manager Name | IDS Contact | Conf Call Setup | Update Event System | PoT Catalog Update
Complete | RL01 | BDD for Compliance | 2006-03-15 | 2006-03-15 | 2006-03-15 | N | 2006-03-15 | 2006-02-22 | 2006-02-22 | 2006-02-22 | 2006-03-01 |  | Robert W Bogan | Robert W Bogan | Lindy Legler | 3/8/06 N | Business Driven Development for Compliance | N
Active | RL02 | Ensuring System Peformance with Rational and Tivoli | 2006-03-27 | 2006-03-27 | 2006-03-27 |  | 2006-03-27 | 2006-03-16 | 2006-03-16 | 2006-03-16 | 2006-03-24 |  | Susann Ulrich/Boca Raton/IBM@IBMUS |  |  | 2006-03-30
| RL03 | GDD | 2006-04-06
| RL04 | BDD for SOA
Complete | RCEP1 | Compliance
Complete | REOT1 | BDD fo SOA | 2006-02-24 | 2006-02-24 | 2006-02-24 | N | 2006-02-24 | 2006-02-24 | 2006-02-24 | 2006-02-24 | 2006-02-24 |  | Robert W Bogan Anshu Prasad |  | Lindy | 2006-03-10 | N Business Driven Development for SOA | N

## WPLC
WPLC
Status | Project # | Project Name | Presentation Workbook Pub Date | Lab WorkBook Pub Date | Images Pub Date | AV Demo | Instructor's Guide | Launch prz Pub Date | Flyer | Abstract | Announce Date | PSN | Resource name | Manager Name | IDS Contact | Conf Call Setup | Update Event System | PoT Catalog Update
Complete | WP1 | WCM | 2005-12-05 | 2005-12-05 | 2005-12-05 | N/A | 2005-12-05 | 2005-12-05 | 2005-11-12 | 2005-11-05 | 2005-12-09 |  | Joe Breal | Heid lundquest | Wendell Crosley | 2005-12-13 | 2005-11-14 | 2005-12-09
Active | WebSphere - Portal
Active | Workplace 2.6 | Workplace 2.6 | 2006-03-20 | 2006-03-20 | 2006-03-20 | N/A | 2006-03-20 | 2006-03-20 | 2006-03-20 | 2006-03-20 | 2006-03-15 |  | Laurisa | Heidi |  | 2006-03-20 | Y | N
Active | zPortal | zPortal
Complete | Workplace Forms EoT | Workplace Forms EoT | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | ???? | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02 | 2006-02-02

## LastSheet
Status
Active
Planned
Complete
Cancelled