## Overall Project Plan
Project Plan
| Time | Task | Owner
Part I
2006-03-27 | 9:00 AM - 09:15 AM | Project Kick off | Feridon Farokhnia
| 09:15 AM - 10:00 AM | Software Academy Overview | Catherine Sollazo
| 10:00 AM - 1100 AM | Software Live | Megan
| 11:00 AM - 04:00:PM | EoT Discussion/Planning | All
| 04:00 PM - 05:00 PM | Enablement Plan/Awareness | All
2006-03-28 | 09:00 AM - 05:00PM | Content Building
2006-03-29 | 09:00 AM - 05:00PM | Content Building
2006-03-30 | 09:00 AM - 05:00PM | Content Building
2006-03-21 | 09:00 AM - 05:00PM | Review the week | ALL
Part II
Week of 4/3/2006 | Fine tuning the Content
Part III
Dry Run
2006-04-10 | 08:00 - 12:00 PM | User Experience
| 12:00 - 01:00 PM | Development
2006-04-11 | 08:00 - 12:00 PM | Business Integration
| 12:00 - 01:00 PM | IT Service Management
2006-04-12 | 08:00 - 12:00 PM | Infrastructure Foundation
| 12:00 - 01:00 PM | Information Services
2006-04-13 | 09:00 - 12:00 PM | Round Table
Phase IV
CSSR Enablement
2006-05-01

## Development
Exploration of Technology: Development Solution
Tasks | Start | Scheduled / Actual Finish | Resource
Identify Resources
Requirements gathering
Developing Presentation
Content Framework Based on the Whitepaper
Identify Case Studies
Identify Demos
Finalize Presentation Including Speaker notes
Finalize Case Studies
Requirements gathering for CEP
Camtasia Presentations
Finalize Abstract
Finalize Flyer
Finalize Instructors handbook
CSSR Enablement
Publication |  | 2006-04-28
Publish Material to the web site
Target Completion date and publication by 4/28

## Business Integration
Exploration of Technology: Business Integration Solution
Tasks | Start | Scheduled / Actual Finish | Resource
Identify Resources
Requirements gathering
Developing Presentation
Content Framework Based on the Whitepaper
Identify Case Studies
Identify Demos
Finalize Presentation Including Speaker notes
Finalize Case Studies
Requirements gathering for CEP
Camtasia Presentations
Finalize Abstract
Finalize Flyer
Finalize Instructors handbook
CSSR Enablement
Publication |  | 2006-04-28
Publish Material to the web site
Target Completion date and publication by 4/28

## IT Service Management
Exploration of Technology: IT Service Management Solution
Tasks | Start | Scheduled / Actual Finish | Resource
Identify Resources
Requirements gathering
Developing Presentation
Content Framework Based on the Whitepaper
Identify Case Studies
Identify Demos
Finalize Presentation Including Speaker notes
Finalize Case Studies
Requirements gathering for CEP
Camtasia Presentations
Finalize Abstract
Finalize Flyer
Finalize Instructors handbook
CSSR Enablement
Publication |  | 2006-04-28
Publish Material to the web site
Target Completion date and publication by 4/28

## Infrastructure Foundation
Exploration of Technology: Infrastructure Foundation Solution
Tasks | Start | Scheduled / Actual Finish | Resource
Identify Resources
Requirements gathering
Developing Presentation
Content Framework Based on the Whitepaper
Identify Case Studies
Identify Demos
Finalize Presentation Including Speaker notes
Finalize Case Studies
Requirements gathering for CEP
Camtasia Presentations
Finalize Abstract
Finalize Flyer
Finalize Instructors handbook
CSSR Enablement
Publication |  | 2006-04-28
Publish Material to the web site
Target Completion date and publication by 4/28

## Information Services
Exploration of Technology: Information Services Solution
Tasks | Start | Scheduled / Actual Finish | Resource
Identify Resources
Requirements gathering
Developing Presentation
Content Framework Based on the Whitepaper
Identify Case Studies
Identify Demos
Finalize Presentation Including Speaker notes
Finalize Case Studies
Requirements gathering for CEP
Camtasia Presentations
Finalize Abstract
Finalize Flyer
Finalize Instructors handbook
CSSR Enablement
Publication |  | 2006-04-28
Publish Material to the web site
Target Completion date and publication by 4/28

## User Experience
Exploration of Technology: User Experience Solution
Tasks | Start | Scheduled / Actual Finish | Resource
Identify Resources
Requirements gathering
Developing Presentation
Content Framework Based on the Whitepaper
Identify Case Studies
Identify Demos
Finalize Presentation Including Speaker notes
Finalize Case Studies
Requirements gathering for CEP
Camtasia Presentations
Finalize Abstract
Finalize Flyer
Finalize Instructors handbook
Publication |  | 2006-04-28
Publish Material to the web site
Target Completion date and publication by 4/28

## SWL
Software Live
Tasks | Start | Scheduled / Actual Finish | Resource
Executive Kick Off
Proving the Business Value of SOA
Software Live! For SOA
Software Strategy |  |  | Taken from current IBM Software Live!
Infrastructure Foundations |  |  | Alan (John McD in charge of Solution EoT)
Business Integration |  |  | Alan (In charge of solution EoT)
Information Services |  |  | Megan (in Charge of Solution EoT)
User Experience |  |  | Megan (Feridon in charge of Solution EoT)
IT Service Management |  |  | Jeff (Catherine in charge of Solution EoT)
Development |  |  | Jeff (In charge of Solution EoT)

## Overall Project Progress
Exploration of Technology Progress
EoT Title | % Completed
User Experience | 0
Information Services | 0
Business Integration | 0
Infrastructure Foundation | 0
IT Service Management | 0
Development | 0
CSSR Enablement | 0